## Sheet1
Moving Cross Country Project Plan Super List - by GreenEyedGuide (Danielle Robertson Rath)
Task Name | Duration | Start | Finish | Deadline | Predecessors | Outline Level
House of Rath | 84.33 days? | Tue 8/8/17 | Wed 10/11/17 | NA |  | 1
Mortage Details | 50 days? | Tue 8/8/17 | Thu 9/14/17 | NA |  | 2
Mail check for Earnest Money | 2 days | Tue 8/8/17 | Wed 8/9/17 | Wed 8/9/17 |  | 3
Envoy paperwork - round 1 | 3 days | Tue 8/8/17 | Thu 8/10/17 | NA |  | 3
Book Home Inspector | 2 days | Tue 8/8/17 | Wed 8/9/17 | NA |  | 3
Review Envoy Plans | 2 days | Tue 8/8/17 | Wed 8/9/17 | NA | 3FF | 3
determine down payment/% | 1 day | Wed 8/9/17 | Thu 8/10/17 | NA | 6 | 3
Mortgage Consulting | 1 day | Thu 8/10/17 | Thu 8/10/17 | NA | 7 | 3
Confirm payment with Envoy | 1 day? | Thu 8/10/17 | Thu 8/10/17 | NA | 7 | 3
Underwriting / Paperwork Review Period - submit any missing docs | 28 days | Fri 8/11/17 | Thu 8/31/17 | NA | 8 | 3
Confirm Home Insurance | 1 day | Fri 9/1/17 | Fri 9/1/17 | NA | 10 | 3
Waiting For Closing Date - Envoy does its thing | 16 days | Fri 9/1/17 | Wed 9/13/17 | NA | 11 | 3
Envoy paperwork - final | 1 day | Wed 9/13/17 | Thu 9/14/17 | NA | 12 | 3
submit down payment at Closing Appt | 0 days | Thu 9/14/17 | Thu 9/14/17 | NA | 13 | 3
Tell Fam/Friends | 7.47 days | Wed 8/9/17 | Tue 8/15/17 | NA |  | 2
Cross Country Coordination | 38.75 days | Tue 8/8/17 | Wed 9/6/17 | NA |  | 2
Shop rates for trucks, POD, towing cars | 1 day | Tue 8/8/17 | Tue 8/8/17 | NA |  | 3
Schedule Penske truck | 1 day | Sat 8/12/17 | Sun 8/13/17 | NA |  | 3
Create driving game plan (route, pit stops for the night) | 5 days | Sat 9/2/17 | Wed 9/6/17 | NA | 58FS-7 days | 3
Streamlining | 35.47 days | Tue 8/8/17 | Sun 9/3/17 | NA |  | 2
Ask around and donate balance beam | 3 days | Tue 8/15/17 | Thu 8/17/17 | NA | 15 | 3
Ask Erin if she has moving boxes | 1 day | Fri 8/11/17 | Sat 8/12/17 | NA | 15 | 3
aquire moving boxes | 20 days | Sat 8/12/17 | Sun 8/27/17 | NA | 30 | 3
Go through lose material in garage | 5 days | Sun 8/27/17 | Wed 8/30/17 | NA | 31 | 3
separate Kitchen Ryan v Rath | 5 days | Wed 8/30/17 | Sun 9/3/17 | NA | 32 | 3
Ask Scott if he wants to take Pheonix | 3 days | Tue 8/8/17 | Thu 8/10/17 | NA |  | 3
Packing | 13.5 days | Sun 8/27/17 | Wed 9/6/17 | NA | 31 | 2
Get box or foam for TVs | 2 days | Wed 8/30/17 | Fri 9/1/17 | NA | 31FS+5 days | 3
Garage - lose ends | 2 days | Wed 8/30/17 | Fri 9/1/17 | NA | 32 | 3
Pantry (game closet + frog cage area) | 1 day | Fri 9/1/17 | Sat 9/2/17 | NA | 37 | 3
Kitchen - shot glasses shelf | 1 day | Sat 9/2/17 | Sat 9/2/17 | NA | 38 | 3
Living Room Non-essentials (movies, table, TV cupboard) | 1 day | Sun 9/3/17 | Mon 9/4/17 | NA | 47 | 3
Garage - book shelf | 1 day | Sun 9/3/17 | Mon 9/4/17 | NA |  | 3
Bedroom bookshelf/under bed | 1 day | Mon 9/4/17 | Tue 9/5/17 | NA | 41 | 3
Kitchen Non-essentials : dishes, pots, pans | 0.5 days | Tue 9/5/17 | Tue 9/5/17 | NA | 42 | 3
Bathroom Non-essentials | 0.5 days | Tue 9/5/17 | Wed 9/6/17 | NA | 45 | 3
Danielle Clothes | 0.5 days | Tue 9/5/17 | Tue 9/5/17 | NA | 43 | 3
Game Room | 1 day | Mon 9/4/17 | Tue 9/5/17 | NA | 40 | 3
Chris Clothes | 1 day | Sat 9/2/17 | Sun 9/3/17 | NA | 39 | 3
Living Room TV and consoles | 1 day | Sun 8/27/17 | Sun 8/27/17 | NA |  | 3
Décor (pictures, bathroom candles) | 1 day | Sun 8/27/17 | Sun 8/27/17 | NA |  | 3
Pack all the essentials (bathroom, kitchen, food, clothes) | 1 day | Sun 8/27/17 | Sun 8/27/17 | NA |  | 3
Final Sweep for any unpacked items | 1 day | Sun 8/27/17 | Sun 8/27/17 | NA |  | 3
Cleaning | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA | 58 | 2
Bathroom | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA |  | 3
Kitchen (excluding floors) | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA |  | 3
Walls (esp Gjalla's scratching post) | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA |  | 3
Kitchen/Dining floors | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA |  | 3
Living Room floors | 2 days | Thu 9/7/17 | Sat 9/9/17 | NA |  | 3
Preparation to Leave | 40.75 days | Tue 8/8/17 | Thu 9/7/17 | NA |  | 2
Confirm date of departure with family/moving company/landloard | 1 day | Tue 8/15/17 | Tue 8/15/17 | NA | 15 | 3
Request time off for driving days | 0.5 days | Tue 8/8/17 | Tue 8/8/17 | NA |  | 3
Get Civic 5K mile checkup before road trip | 1 day | Tue 8/29/17 | Wed 8/30/17 | NA |  | 3
Make arrangements for any meetings on Moving Truck Loading Day | 0.5 days | Wed 8/30/17 | Wed 8/30/17 | NA | 61 | 3
Make arrangements for any meetings on Driving/Arrival Day | 0.5 days | Wed 8/30/17 | Thu 8/31/17 | NA | 62 | 3
Weekend Trip with Family | 3 days | Sat 9/2/17 | Mon 9/4/17 | NA | 63FS+3 days | 3
Last Hangout with Kerri | 1 day | Mon 9/4/17 | Tue 9/5/17 | NA | 64 | 3
Last hangout with Erin | 1 day | Tue 9/5/17 | Wed 9/6/17 | NA | 65 | 3
Last trips to the dog beach | 7 days | Wed 8/30/17 | Mon 9/4/17 | NA | 61 | 3
Assemble road snacks and tunes | 1 day | Mon 9/4/17 | Tue 9/5/17 | NA | 64 | 3
pick up Penske/Budget truck | 0.25 days | Thu 9/7/17 | Thu 9/7/17 | Thu 9/7/17 |  | 3
load vehicles | 0.5 days | Thu 9/7/17 | Thu 9/7/17 | NA | 69 | 3
LEAVE SO CAL | 0 days | Thu 9/7/17 | Thu 9/7/17 | NA | 58FS+1 day | 2
Leaving | 12.25 days | Thu 9/7/17 | Sat 9/16/17 | NA |  | 2
leave HB | 1 day | Thu 9/7/17 | Fri 9/8/17 | NA | 70 | 3
HB to PW | 4 days | Fri 9/8/17 | Mon 9/11/17 | NA | 73 | 3
arrive PW | 1 day | Mon 9/11/17 | Tue 9/12/17 | Sun 9/17/17 | 74 | 3
Final Walk-through and get keys | 0.5 days | Thu 9/14/17 | Thu 9/14/17 | NA | 75FS+3 days | 3
unload | 1 day | Thu 9/14/17 | Fri 9/15/17 | NA | 76 | 3
Pick up new furniture/hand-me downs with moving truck | 2 days | Fri 9/15/17 | Sat 9/16/17 | NA | 77 | 3
return truck | 0.25 days | Sat 9/16/17 | Sat 9/16/17 | Thu 9/14/17 | 78 | 3
FIRST NIGHT IN NEW HOUSE | 0 days | Thu 9/14/17 | Thu 9/14/17 | Thu 9/14/17 |  | 2
Transitions | 15 days | Thu 9/7/17 | Mon 9/18/17 | NA | 58 | 2
schedule 3 local events | 15 days | Thu 9/7/17 | Mon 9/18/17 | NA |  | 3
Meet 3 neighbors | 15 days | Thu 9/7/17 | Mon 9/18/17 | NA |  | 3
Schedule House Warming pot-luck | 15 days | Thu 9/7/17 | Mon 9/18/17 | NA |  | 3
Logistics and Mailing | 73.58 days | Wed 8/16/17 | Wed 10/11/17 | Thu 9/14/17 | 71FS-30 days | 2
get Gjalla's heartworm and Joint meds | 1 day | Wed 8/16/17 | Thu 8/17/17 | NA |  | 3
terminate current dentist | 1 day | Wed 8/16/17 | Wed 8/16/17 | NA | 89 | 3
change address US Postal | 10 days | Wed 8/16/17 | Thu 8/24/17 | NA | 90 | 3
Update Southwest Address | 1 day | Wed 8/16/17 | Wed 8/16/17 | NA |  | 3
change flights to New York | 2 days | Sat 9/2/17 | Sun 9/3/17 | NA | 97 | 3
update Triple A address (via Transfer Request) | 5 days | Fri 8/25/17 | Mon 8/28/17 | NA | 104 | 3
update US Bank addy | 1 day | Sun 9/3/17 | Mon 9/4/17 | NA | 93 | 3
set up internet/cable | 3 days | Mon 9/11/17 | Wed 9/13/17 | NA | 81FS-3 days | 3
set up electricity | 3 days | Wed 9/13/17 | Fri 9/15/17 | NA | 81FS-1 day | 3
update cell phone plan | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
update Ralphs | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
update Student Loans | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
update Banfield | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
find new vet (?) | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
Schedule appt with new DMV for new DL | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
update voter registration | 5 days | Fri 10/6/17 | Wed 10/11/17 | NA | 103 | 3
Update Kohls | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
Update Target | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
Update prescriptions | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
Find new primary care | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3
Find new dentist | 30 days | Thu 9/14/17 | Fri 10/6/17 | NA | 81 | 3